## Sheet
|  | Min* | Max*
Ideation | Reference Gathering | 1 | 3
| Concepts | 5 | 10
Design | Implement whitebox | 2 | 3
| Modules planning | 5 | 15
| Material exploration | 4 | 12
Development | Final models | 8 | 30
| Skybox | 2 | 3
| Light pass | 2 | 3
Polish | Optimisation | 1 | 8
| Audio | 1 | 2
| Total days | 31 | 89
| Total weeks | 6.2 | 17.8
| Total months | 1.4091 | 4.0455
*in days per person